## fixes
ID | PRIORITY | AREA | SYMPTOM | ROOT CAUSE | THE FIX | FILES TO CHANGE | COST TO APPLY | IF IT IS SKIPPED | STATUS | DATA ISSUE
F1 | 1 | budget layer / mapping | Brazil's mapped financing is only known to within 1.4 points of the national budget, and one strategy is reported unfunded that is not | The pipeline treats (fiscal_year, program_code) as the key for a budget programme. In Brazil's PPA the same code appears under many budget strategies, each with its own amount, so the key is ambiguous and every consumer resolves it differently: load_budget keeps the last row it read, v_funding_by_program sums them all. | Make (fiscal_year, budget strategy_code, program_code) the unit everywhere. Prompt 6 already sees the budget strategy in its input table and must emit it on the match. build_final_panel.load_budget keys on all three. The Supabase view joins matches to budget_lines on all three. audit_checks A3 changes from 'programme counted once' to 'programme-line counted once'. | 01_Pipeline/prompts/6_mapping.txt, 01_Pipeline/scripts/build_final_panel.py (load_budget, funding_by_program), 03_Ingest_and_Publishing/supabase/migrations/0005_*.sql, 01_Pipeline/scripts/audit_checks.py | Re-run Prompt 6 for Brazil, 4 budget years. Thailand and Brunei are unaffected (their codes are unique) but should be re-run for one panel shape. | Every Brazil money figure carries an unquantified 4.5% ambiguity and one strategy is wrongly listed as unfunded. | OPEN
F2 | 1 | Prompt 4, strategy clean | Standing functions are tagged as responses to risks they do not address, inflating every risk chart | Prompt 4 asks which of the eleven risks a strategy relates to and accepts topical adjacency. Nothing requires the plan to say the strategy responds to that risk, and nothing penalises tagging six risks at once. | Require, for each risk named, a verbatim quotation from that strategy's own text that states the connection, emitted in a risk_evidence field beside related_risks. Cap at three risks unless the plan explicitly names more. Say that a standing function of the state (defence, debt service, pensions, general administration) is not a risk response unless the plan frames it as one. Then a new check, A19, fails any related_risks entry with no quotation behind it, which makes the rule enforceable rather than hoped for. | 01_Pipeline/prompts/4_strategy_clean.txt, 02_Automation/schemas.py (STAGE4_FIELDS), 01_Pipeline/scripts/audit_checks.py (A19), 01_Pipeline/scripts/build_final_panel.py (carry risk_evidence) | Re-run stage 4 for all three countries. Stage 4 is the judgement stage, so this is the expensive one; roughly the cost of a full re-run of consolidation per country. | Every risk chart on every page overstates how much of the budget responds to each risk, and the error is invisible to every existing check. | OPEN
F3 | 2 | Prompt 5, budget extraction | Brunei yields one usable budget year out of four documents, and budget line names leak into the strategy inventory | Brunei's budget is a speech, not a table. Prompt 5 is written for a tabulated budget: it looks for programme rows with codes and amounts, finds few, and the gap is then filled from the budget side of the mapping, which puts budget line names into the strategy column. | A second budget-extraction prompt for narrative budgets, selected per country by a documents.style flag in the country config. It reads prose ('The amount of X million will be allocated to Y'), emits the same schema, and marks each row with the sentence it came from so source fidelity can still check it. China's budget has the same shape, so the prompt is needed twice over. | 01_Pipeline/prompts/5b_budget_transcript.txt (new), 02_Automation/stages.py (stage 5 selects the prompt), 01_Pipeline/countries/*.json (documents.style) | One new prompt plus a re-run of stage 5 for Brunei's four documents. | Brunei stays a one-year country and its 97.4% coverage figure keeps resting on a single speech. | OPEN
F4 | 3 | Prompt 3, intervention extraction | 11.5% of intervention_evidence quotations are paraphrases rather than the plan's own words | Prompt 3 asks for evidence and does not say that the evidence must be a substring of the source. The model summarises where the sentence is long. | State that intervention_evidence must be copied character for character, and that a quotation that cannot be copied verbatim should be shortened rather than reworded. validate_evidence_quotes already measures this, so the fix is verifiable the moment it runs. | 01_Pipeline/prompts/3_strategy_extraction.txt | Re-run stage 3 per country. | A reviewer checking a quotation against the plan finds words that are not there and stops trusting the rest. | OPEN
F5 | 3 | Supabase | maturity_summary has no view behind it, so the database cannot reproduce six of its eight metrics | 0004_maturity_subtypes.sql was written and never applied: it needs either a service token or a paste into the SQL editor. | Apply the migration, then confirm audit_checks A12 and build_dashboard_from_db --verify agree with the sheet. | 03_Ingest_and_Publishing/supabase/migrations/0004_maturity_subtypes.sql | None beyond applying it. | The database round trip stays unfaithful for the maturity metrics. | FIXED
F6 | 1 | Prompt 4, strategy clean | Budget programme names come back out of stage 4 as plan strategies, then match 'their' programme perfectly | run_stage4 injects the budget programme list into Prompt 4 as the target granularity, which is right: it is how a strategy lands on a fundable unit. But nothing forbids the model from ANSWERING with a bucket name when it has no plan material to consolidate. Brunei's NDP text is a speech, stage 3 recovers little, and four strategies came back that are budget lines wearing a strategy's clothes. | Two lines in Prompt 4: a strategy must consolidate at least one intervention from the row-level table, and the budget programme list is a target to map ONTO, never a source to draw names from. Check A18 already fails any strategyclean row with no component intervention, so the rule is enforced rather than hoped for. A18 is advisory today; promote it to a gate once Brunei is re-run. | 01_Pipeline/prompts/4_strategy_clean.txt, 01_Pipeline/scripts/audit_checks.py (A18, already added) | Re-run stage 4 for Brunei. Thailand and Brazil already pass A18, so they need no re-run for this. | Brunei's page shows budget lines as plan strategies with confident rationales, and its 97.4% of budget mapped is partly the budget matching itself. | OPEN
F7 | 1 | Prompt 5, budget extraction | Two countries' budget figures come from a prompt version that has been superseded | Prompt 5 gained rules 3a and 4a on 2026-08-12 after Thailand's FY2024 was found to be missing programmes 2.14 and 2.15, whose table rows wrap and whose amounts are printed in the narrative. Only Thailand was re-run. Nothing in the pipeline compared an output's date with its prompt's, so the gap was invisible. | Re-run stage 5 for Brazil (2021, 2024) and Brunei (2021, 2022, 2025, 2026), then run_pipeline for both. Detector D12 already reports the condition; promote it to a gate once both are current. | 02_Automation/run_llm_pipeline.py --stages 5 --force, then 01_Pipeline/scripts/run_pipeline.py | Six budget documents through stage 5. Brunei's four are speeches and will still extract poorly until F3 lands, so Brazil's two are the ones that will actually change figures. | Brunei's two unreconciled strategy-years stay unexplained, and Brazil's coverage may be understated by whatever the old prompt skipped. | OPEN
F8 | 1 | Prompt 5, budget extraction | A multi-year project table extracts nothing, because which column is this year's budget is never stated | Prompt 5 assumes a budget table has one amount column and a strategy total to reconcile against. Kiribati's development budget has six year columns and no ministry totals; Thailand's FY2023 book has three. Where the assumption holds the prompt works; where it does not the model correctly declines to guess and the country produces nothing for the price of a full extraction. | Add an optional amount_column to the per-year budget config, passed into Prompt 5 as the column to read ('2025 Budget'), and have the prompt state that where several year columns exist it must use the named one and emit nothing rather than guess. Where no column is named and several exist, stop before spending: document_shape.py already reports the count. The reconciliation rule needs the same treatment, since a table with no printed strategy total cannot reconcile and should say so rather than fail. | 01_Pipeline/prompts/5_budget_extraction.txt, 02_Automation/inputs/<slug>.json (amount_column), 02_Automation/stages.py (pass it through), 01_Pipeline/scripts/document_shape.py (already reports year columns) | One prompt change plus a re-run of stage 5 for Kiribati, four documents, about $2. | Kiribati cannot be run at all, and any country whose budget is published as a multi-year table has the same wall. On the evidence of these ten, that is a common publishing format rather than an oddity. | OPEN
F9 | 1 | orchestration | Countries are committed to a full run before anyone knows whether their budget document can be extracted at all | The only gate before spending was a text heuristic, and it was wrong three times in a row: Malaysia read as prose because its programme codes are six digits, Kiribati read as a usable table when its rows are catering and cleaning, Bhutan read as a usable table when its rows are corporate accounts. Each fix made the heuristic smarter without making it right, because the question is what the PROMPT will find and only the prompt can answer that. | Make stage5_probe.py a required step: one budget document, 4 to 10 calls, programme rows counted per page. Wire it into the orchestrator so a country with no probe result, or a failing one, does not start. Then route by document class, since the probe also tells you WHICH class: estimates table to Prompt 5, narrative to 5b (F3), multi-year project table to 5c or a named amount column (F8), fiscal report to nothing until the right document is sourced. | 02_Automation/stage5_probe.py (written), 02_Automation/run_llm_pipeline.py (gate on it), 02_Automation/inputs/<slug>.json (documents.style) | None to build; it saves $8 to $48 every time a country would have failed. | Kiribati cost $6.21 and Bhutan $2.00 to learn what $0.60 of probing would have said first. | OPEN
F10 | 1 | combine_budget_years | The programme code style is defaulted, and the wrong default silently unmaps a whole country | normalize_program_code assumes hierarchical codes and prefixes a bare code with its strategy. Where codes are standalone the result matches nothing. It cost Brazil 524 edges, then Kenya 824 programme-years and Jamaica 254, each discovered separately after a full run. | Choose the style by measuring rather than defaulting: try both against the mapping's codes and take the one that resolves more, or refuse to build and say which style the codes look like. The evidence is already on disk at build time, so this needs no model call and no new input. Add a check that fails when more than a tenth of a country's matched codes are absent from its own budget layer. | 01_Pipeline/scripts/combine_budget_years.py (normalize_program_code), 01_Pipeline/scripts/audit_checks.py (new check) | None. Deterministic, and it runs on data the pipeline already holds. | Every new country is one silent default away from mapping nothing, and the symptom looks like a bad model rather than a bad join. | OPEN